## Sheet1
MN PDAB WORK PLAN | [6 empty] | 2025-01-13
| 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01
Data Collection/ Drug Review | *MDH drug list received *Identify additional data sources *Identify data staff solution | *Drug review design *Obtain additional data sources *Contract for data staff | *Drug review design | *Identify drugs for review *Drug review design | *Complete drug review design | *Begin drug review | *Ongoing drug review
Infrastructure Development | *State emails and SharePoint access for Board *Ongoing SharePoint/data site development | *Complete SharePoint/data site development | *Populate SharePoint/data sites | *Ongoing SharePoint/data site management | *Ongoing SharePoint/data site management | *Ongoing SharePoint/data site management | *Ongoing SharePoint/data site management
Governance Documents and Training | *First quadrant reviewed *Second quadrant presented to Board | *Review Second quadrant *Third quadrant presented to Board | *Review third quadrant | *Fourth quadrant presented to Board | *Review fourth quadrant | *Approve all four governance quadrants | *Review and approve governance handbook
Patient Outreach | *Virtual listening session | *Listening session planning | *In person listening session | *Listening session planning | *Virtual listening session | *Listening session planning | *In Person listening session