## By Deliverable
Minnesota Community Supervision Advisory Committee (CSAC)
| D1: Statewide Supervision Standards | D2: Risk and Needs Assessment Tools | D3: Assessment-Driven, Collaborative Case Planning | D5: Gender-Responsive, Culturally Appropriate, and Trauma-Informed Services | D6: Statewide Behavior Response Grid | D7: Performance Indicators for Supervision | D8: Statewide Training, Coaching, and Quality Assurance Systems | D10: Plan to Eliminate Financial Penalty for Early Discharge | D11a: Proposed State-Level Community Supervision Advisory Board | D11b: Review and Reassess the Workload Study
| Develop ISR policy | Adopt the LS/CMI as general risk and need assessment tool | Develop policy for case planning with moderate and high-risk clients, use of an automated case plan template in CSTS, and establishing a formalized, evidence-based, case planning process | **Continue work with EBP Statewide Advisory Committee to develop comprehensive and actionable set of recommendations | **Continue work on a comprehensive grid for all 3 systems | DOC is taking steps to produce the first report | Develop policy to require all agencies ensure training, coaching, and QA of 5 EBP skill areas | Require Workload Study researchers to also analyze impact of early discharge and provide tailored recommendations | Expand and revise CSAC membership through legislative change | Continue to work on selecting a vendor and launching study - DOC to fund
Develop IPV policy
|  | Develop policy for use of pre-screener and/or LS/CMI |  |  | Will pursue language change in statute |  |  |  | Expand budget for CSAC through legislative change
Develop policy to require all agencies ensure applicable staff complete initial training w/n 1st year of employment and ongoing training
Develop comprehensive outline for full set of supervision standards
|  | Continue identifying statewide pre-screener for probation clients | [6 empty] | Provide CSAC recommendations to legislature regarding collaborative decision-making and oversight shift
Submit progress report within 1 year of implementation evaluating readiness for moderate risk clients
Develop proposed prioritization and timeline for full set of supervision standards
|  | Continue to consider and make recommendations for supplemental assessments for special populations |  |  |  |  | Seek legislative amendment to change statutory language to "advised by the EBP Statewide Advisory Committee" and revise CSAC charter
Prioritize development of metrics to assess fidelity and outcomes
Validate the LS/CMI and pre-screener
Study and make recommendations for formal integration of MNSTARR 3.0 for supervised release or ISR
Provide additional recommendations for supervision standards for misdemeanors not screened with LS/CMI
Committee Key
JRI Phase II Working Group
Risk and Needs Assessment Working Group
DOC or Legislative Action
EBP Statewide Advisory Committee
Vendor for Validation Work
Vendor for Workload Study
DV/IPV Steering Committee
ISR Transformation Committee

## Sequencing-Mapping
Minnesota Community Supervision Advisory Committee (CSAC)
| March 2025-July 2025 |  | August 2025-December 2025 |  |  |  | January 2026-June 2026 | July 2026 and Beyond
D1: Statewide Supervision Standards
Develop ISR policy
Develop IPV policy
|  | Develop proposed prioritization and timeline for full set of supervision standards |  |  | Provide additional recommendations for supervision standards for misdemeanors not screened with LS/CMI
Develop comprehensive outline for full set of supervision standards
D2: Risk and Needs Assessment Tools
Continue identifying statewide pre-screener for probation clients
Develop policy for use of pre-screener and/or LS/CMI
Adopt the LS/CMI as general risk and need assessment tool
|  | Validate the LS/CMI and pre-screener | [6 empty] | Revalidate LS/CMI and pre-screener every 5 years
Continue to consider and make recommendations for supplemental assessments for special populations
Study and make recommendations for formal integration of MNSTARR 3.0 for supervised release or ISR
D3: Assessment-Driven, Collaborative Case Planning
Develop policy for case planning with moderate and high-risk clients
|  | Develop policy to use automated case plan template in CSTS |  | Prioritize development of metrics to assess fidelity and outcomes |  |  |  | Submit progress report within 1 year of implementation evaluating readiness for moderate risk clients
Develop policy to establish a formalized, evidence-based, case planning process
D5: Gender-Responsive, Culturally Appropriate, and Trauma-Informed Services
**Continue work with EBP Statewide Advisory Committee to develop comprehensive and actionable set of recommendations
D6: Statewide Behavior Response Grid
**Continue work on a comprehensive grid for all 3 systems
Will pursue language change in statute
D7: Performance Indicators for Supervision
DOC is taking steps to produce the first report
D8: Statewide Training, Coaching, and Quality Assurance Systems
Develop policy to require all agencies ensure training, coaching, and QA of 5 EBP skill areas
Develop policy to require all agencies ensure applicable staff complete initial training w/n 1st year of employment
Seek legislative amendment to change statutory language to "advised by the EBP Statewide Advisory Committee" and revise CSAC charter
D10: Plan to Eliminate Financial Penalty for Early Discharge
Require Workload Study researchers to also analyze impact of early discharge and provide tailored recommendations
D11a: Proposed State-Level Community Supervision Advisory Board
Expand and revise CSAC membership through legislative change
Expand budget for CSAC through legislative change
Provide CSAC recommendations to legislature regarding collaborative decision-making and oversight shift
D11b: Review and Reassess the Workload Study
Continue to work on selecting a vendor and launching study - DOC to fund
Committee Key
JRI Phase II Working Group
Risk and Needs Assessment Working Group
DOC or Legislative Action
EBP Statewide Advisory Committee
Vendor for Validation Work
Vendor for Workload Study
DV/IPV Steering Committee
ISR Transformation Committee

## Work Plan
Minnesota Community Supervision Advisory Committee (CSAC) Work Plan
Updated 7/14/2025
Deliverable | Task | Assigned Committee | Status | Key Activities | Challenges/Needs | CSAC Action | Next Steps | Policy Chair | Policy Review Process | Link to Policy (Working Draft) | CSAC Due Date
Deliverable 1: Statewide Supervision Standards | Develop ISR policy | ISR Transformation Committee | Complete | ISR Policy 620.100 has been approved by Commissioner Schnell (6/25/25). 5/12/25 - ISR policy has been approved by CSAC and DOC legal. Policy is slated to be presented to DOC Exec Council 5/20/2025. ISR Conference scheduled for 5/21-5/22 and ISR policy will be presented and skill exercises included to practice new supervision standards. Presented policy draft to CSAC on 2/26/25 with feedback due back to ISR committee by 3/14/25. Updated draft completed 3/18/25 by the ISR Transformation chairs. Additional feedback requested by 04/15/25. | Working on implementation plan for the ISR conference 5/21-5/22. Planning underway for policy rollout. | Policy with feedback to be brought back to CSAC in April. | Review by CSAC and vote in April. | TBD | Second draft completed based on feedback. Submit to CSAC for final review and vote (April). | ISR Transformation Policy Drafts | 2025-07-01
| Develop IPV policy | DV/IPV Steering Committee | In Progress | We have been working on the draft policy and continue to do so. We met on July 1, will meet again on July 28, and are hoping to get final approval from the entire DVSC on our meeting on August 5th 6/9/25 - The DVSC met at the beginning of the month and discussed the proposed policy. The information from the discussion is being compiled and at least a preliminary draft should be ready by the end of July. 5/8/25 - The policy proposal for the IPV Reunification Guidance is on the agenday for the DVSC. Initial draft is anticipated to be ready for CSAC by the end of June. CSAC members and CSG Justice Center staff will meet with DV Steering Committee chairs in April to clarify roles | We had planned to begin this work in May, but other issues took precedence. We began the work on our June monthly call (6/3/2025) and plan to complete it on our July call (7/1/2025). | March - Approved members and CSG Justice Center staff to meet with DV Steering Committee to clarify roles. Will report back in April. | Plan to deliver a final draft to CSAC on August 6th Meeting scheduled to outline task from CSAC | TBD | TBD | TBD | 2025-07-01
| Develop comprehensive outline for full set of supervision standards | JRI Phase II Working Group | In Progress | Members of the JRI group will begin review of APPA standards in preparation of our meeting in August. 5/2/25 - Received research and working documents from CSG. Materials are being reviewed for future actions. CSG Justice Center staff is in the process of compiling and analyzing CCA, CPO, and DOC supervision policies. CSG Justice Center staff plans to share this progress with MN Phase II WG members on 3/25 outlining consistencies, gaps, and trends across policies. | Supervision policies are still needed for: CCA: Carlton, Cook, Dakota, Dodge, Fillmore, Isanti, Kandiyohi, Koochiching, Lac Qui Parte, Lake, Nicollet, Nobles, Norman, Olmstead, Polk, Red Lake, Rice, Rock, Scott, St. Luis, Stearns, Swift, Todd, Wadena, Washington, Yellow Medicine CPO: Big Stone, Cass, Chisago, Freeborne, Goodhue, Grant, Itasca, Jackson, Kanabec, Stevens, Traverse, Wabasha, Wilkin, Wright | None noted | The MN JRI II Working group met 6/6/25 to discuss leadership and tasks needed. Supervision policies will be compiled with consistencies, gaps, and trends outlined and targeted for alignment. | N/A | N/A | N/A | No End Date
| Develop proposed prioritization and timeline for full set of supervision standards | JRI Phase II Working Group | In Progress | We will dive in to this more after review of APPA standards. We anticipate needing the rest of 2025. Supervision policies are being compiled. | None noted | None noted | Will outline timeline once trends are identified and targeted for alignment. | N/A | N/A | N/A | No End Date
Deliverable 2: Risk and Needs Assessment Tools | Adopt the LS/CMI as general risk and need assessment tool | Risk and Needs Assessment Working Group | Complete | LS/CMI is pending validation with the selected vendor | Update on vendor contract is needed | None noted | LS/CMI is pending validation with the selected vendor | N/A | N/A | N/A | Complete
| Develop policy for use of pre-screener and/or LS/CMI | Risk and Needs Assessment Working Group | In Progress | RNA Working Group to define the scope and application criteria for a statewide policy on the use of a pre-screener and/or LS/CMI, focusing on aligning tool usage with offense categories and ensuring system-wide consistency across delivery systems CSG Justice Center staff is actively collaborating with the RNA Working Group to define the scope and application criteria for a statewide policy on the use of a pre-screener and/or LS/CMI, focusing on aligning tool usage with offense categories and ensuring system-wide consistency across delivery systems. | The Risk and Needs Working group met on 6/13/25 and discussed leadership and task needed. May need an extension and request policy draft date of September. Would like to request a copy of blank policy draft and any relevant guidance from DOC Policy Department | None noted | The Risk and Needs Working group met on 6/13/25 and discussed leadership and taks needed. Advance policy development by defining criteria for pre-screener and LS/CMI application across offense levels, and begin stakeholder review and feedback. Further discussion will take place during 3/20 WG meeting. | TBD | TBD | TBD | Policy framework/structure draft due in July 2025. Full policy due at a later date.
| Continue identifying statewide pre-screener for probation clients | Risk and Needs Assessment Working Group | In Progress | CSG Justice Center staff met with the Pre-Screener Subcommittee on 1/14 to assess Minnesota’s readiness to develop a statewide pre-screener, confirming that while DOC and counties have robust data infrastructure, additional resources and further clarification from RNA WG members will be needed for creation of a MN statewide pre-screener. Committee is evaluating if having a vendor develop the pre-screener is preferable to developing with inter-agency staff. | None noted | None noted | Continue evaluating pre-screener development options, validate feasibility for CSTS integration, and assess the potential to leverage existing LS/CMI validation data through the current vendor to support tool development. | N/A | N/A | N/A | 2026-01-01
| Continue to consider and make recommendations for supplemental assessments for special populations | Risk and Needs Assessment Working Group | In Progress | RNA Working Group to develop and finalize a comprehensive document that captures all offense-specific and trailer risk and needs assessment tools currently in use across Minnesota’s supervision delivery systems and best practices in the field. This document details the predictive accuracy, administration time, and costs for each tool and will serve as a critical resource to help Minnesota determine which tools should be approved for use statewide across all delivery systems. CSG Justice Center staff is working closely with the RNA Working Group to develop and finalize a comprehensive document that captures all offense-specific and trailer risk and needs assessment tools currently in use across Minnesota’s supervision delivery systems and best practices in the field. This document details the predictive accuracy, administration time, and costs for each tool and will serve as a critical resource to help Minnesota determine which tools should be approved for use statewide across all delivery systems. Further discussion will take place during 3/20 WG meeting. | The Risk and Needs Working group met on 6/13/25 and discussed leadership and task needed. May need an extension and request policy draft date of September. | None noted | Finalize the document with RNA Working Group input and present it to CSAC to recommend a standardized set of validated tools for statewide use across all supervision delivery systems. | N/A | N/A | N/A | No End Date
| Validate the LS/CMI and pre-screener | Vendor for LS/CMI Validation | In Progress | Awaiting contract execution with selected vendor |  | None noted | Validation work to begin once contract is executed | N/A | N/A | N/A | No End Date
| Study and make recommendations for formal integration of MNSTARR 3.0 for supervised release or ISR | JRI Phase II Working Group | Not Started | None at this time | None noted | None noted | Assigned to JRI Phase II WG after March CSAC meeting | N/A | N/A | N/A | No End Date
| Provide additional recommendations for supervision standards for misdemeanors not screened with LS/CMI | JRI Phase II Working Group | Not Started | Subgroup met on 6/13 - Julie Rud gave an update on pre-screener and discussed that they looked at the Oregon Public Safety Checklist for guidance. | None noted | None noted | None noted | N/A | N/A | N/A | No End Date
| Re-validate LS/CMI and pre-screeners every 5 years | Vendor for LS/CMI Validation | Not Started | Awaiting contract execution with selected vendor | None noted | None noted | Awaiting contract execution for original validation study | N/A | N/A | N/A | 5 years after initial validation
Deliverable 3: Assessment-Driven, Collaborative Case Planning | Develop policy for case planning with moderate and high-risk clients, automated case plan template in CSTS, and establishing a formalized, evidence-based, case planning process | JRI Phase II Working Group | In Progress | Case planning policy draft was submitted to the JRI Phase 2 group and MACCAC Directors for review. It is included in the packet for the meeting. Framework has been developed with rationale/research, proposed metrics for success, implementation considerations, and technology needs. WG will continue building out the framework to drive policy development. Subaward is approved and work has begun on technology enhancements in coordination with STI. | Creating a policy that was broad enough was tricky. We also received lots of feedback that we tried to incorporate | None noted | Framework and policy will continue to be developed at subcommittee level and monthly WG meetings. | TBD | TBD | TBD | Policy framework/structure draft due in July 2025. Full policy due at a later date.
| Prioritize development of metrics to assess fidelity and outcomes | JRI Phase II Working Group | In Progress | CSTS enhancements are on hold as there are other prioritized enhancements. A document related to that subgroups work is included in the packet. Initial framework developed around assessment-driven case planning with initial data metrics identified. WG continues to work with the CSTS Data Committee and other relevant committees to identify metrics. | Coordination will need to continue between the committees. | None noted | Discussion will continue at monthly WG meetings, as policy is developed. | N/A | N/A | N/A | No End Date
| Submit progress report within 1 year of implementation evaluating readiness for moderate risk clients | JRI Phase II Working Group | Not Started | This is partly addressed in the policy | None noted | None noted | None noted | N/A | N/A | N/A | 1 year after implementation
Deliverable 5: Gender-Responsive, Culturally Appropriate, and Trauma-Informed Services | **Continue work with EBP Statewide Advisory Committee to develop comprehensive and actionable set of recommendations | EBP Statewide Advisory Committee | Not Started | Draft recommendations provided to the EBP Advisory. Feedback being generated from meeting and offline comments. Increased membership with MACCAC Gender Equity representatives and Amber Brown (CSAC lived experience rep). Reviewed Gender-Responsive Assessment to identify “low hanging fruit” that could inform recommendations for CSAC Committee met with Christine Cicero who provided an overview of her work and an assessment tool agencies can use to evaluate gender, trauma and cultural responses, policies and procedures. Subcommittee will do a practice run utilizing the assessment tool to identify what we learn that can serve as a way to guide us towards recommendations. The EBP Advisory Committee has established a subcommittee to address this deliverable. The first meeting is scheduled March 25th to begin the work. Ross Becker (Wright Co), Nick Krueger (DOC), Tracy Zabel (Rice Co) and Jen Lamppa (ARC) are the established members. Currently reviewing literature and sharing amongst the group to prepare for the first meeting. | Sub-committee will meeting in July to review comments and provide adjustment to recommendations. Determining state-wide recommendations pose a challenge due to local resources and staffing. Timeline to provide recommendation by June (for July) is approaching. We are also adding additional members from the MACCAC Race Equity Committee to better incorporate the work already done through MACCAC. | March 2025 - Clarified that the policies noted in Deliverables 1-4 are higher priority. Framework is appropriate for July 2025. | Will seek feedback as needed. Committee establishment in March. | TBD | TBD | TBD | 2026-12-31
| Establish a baseline training for supervision probation staff on gender-responsiveness, cultural competency, and trauma-informed approaches for all agencies, with flexibility for agencies to select ongoing training that aligns with the unique needs of their communities | EBP Statewide Advisory Committee | In Progress | Draft recommendations provided to the EBP Advisory. Feedback being generated from meeting and offline comments. Gender-Responsive Assessment has provided the group understanding where this can be established and the types of trainings to incorporate. Presented at the EBP Advisory and questioned our current “core” EBP curriculums and incorporation of gender/trauma/culture focus through skill practices and training. | Sub-committee will meeting in July to review comments and provide adjustment to recommendations. If approved, time will be needed for agencies to incorporate into onboarding locally. May be a challenge with differing curricula that isn’t “hitting the mark”. | [5 empty] | 2025-07-23
Deliverable 6: Statewide Behavior Response Grid | **Continue work on a comprehensive grid for all 3 systems | JRI Phase II Working Group | Framework is in progress | The subgroup presented a memo with recommendations for this deliverable at our meeting. The memo is included in the packet. Initial framework developed around a simple behavior response grid. CSG Justice Center staff met with MRRA rep Kate Frykman on 3/5 to identify how to best support work between the two committees. Subcommittee formed in March. | None noted | March 2025 - Timeline for framework is appropriate based on subcommittee formation in March. Committee should raise red flag in May/June if timeline appears to be too aggressive. Important to include a menu of options for agencies/jurisdictions to choose from. | Discussion will continue at monthly WG meetings, as policy is developed. | TBD | TBD | TBD | 2025-07-01
| Will pursue language change in statute | Legislative Change - No Committee Assigned | In Progress | None at this time | None noted | March 2025 - Language changes communicated to legislature but DOC cannot communicate | None noted | N/A | N/A | N/A | No End Date
Deliverable 7: Performance Indicators for Supervision | DOC is taking steps to produce the first report | DOC - No Committee Assigned | In Progress | None at this time | None noted | None noted | None noted | N/A | N/A | N/A | No End Date
Deliverable 8: Statewide Training, Coaching, and Quality Assurance Systems | Develop policy to require all agencies ensure training, coaching, and QA of 5 EBP skill areas | EBP Statewide Advisory Committee | In Progress | The sub-committee of the EBP Statewide Advisory Committee (SAC) presented the recommendations to the larger EBP SAC. Updates to the recommendations were made. The EBP SAC are ready to present on the recommendations thus far. Our sub-committee is currently working on a policy draft, and we are getting ready to present it to the main EBP Statewide Advisory Committee on 06/30/2025. Reviewed CSAC recommendations and the Commissioner's response. Discussed what is needed going forward. | Needs: Clarification regarding coaching and QA and what that might look like in policy | Questions for CSAC: -How to address differences in CSAC's original recommendation versus the Commissioner's response as it related to coaching and QA? -How specific does CSAC want the policy to be regarding coaching and QA? | Next Steps: Review CSAC's feedback, meet with DOC policy team member, possibly start on draft policy | TBD | No drafts completed at this time | TBD | 2025-07-01
| Develop policy to require all agencies ensure applicable staff complete initial training within 1st year of employment and ongoing training | EBP Statewide Advisory Committee | In Progress | The sub-committee of the EBP Statewide Advisory Committee (SAC) presented the recommendations to the larger EBP SAC. Updates to the recommendations were made. The EBP SAC are ready to present on the recommendations thus far. Our sub-committee is currently working on a policy draft, and we are getting ready to present it to the main EBP Statewide Advisory Committee on 06/30/2025. Reviewed CSAC recommendations and the Commissioner's response. | Was the intent of this policy for Supervisors/Directors to complete the required training as well? | None noted | Next subcommittee meeting is June 5th to finalize draft and then present it to the large EBP Statewide Advisory Committee on June 30th | TBD | No drafts completed at this time | TBD | 2025-07-01
| Seek legislative amendment to change statutory language to "advised by the EBP Statewide Advisory Committee" and revise CSAC charter | EBP Statewide Advisory Committee | In Progress | None at this time | None noted | None noted | None noted | N/A | N/A | N/A | No End Date
Deliverable 10: Plan to Eliminate Financial Penalty for Early Discharge | Require Workload Study researchers to also analyze impact of early discharge and provide tailored recommendations | Vendor for Workload Study | In Progress | Leadership committee has met three times to identify supervision standards, case types and policy/procedure guidelines of agencies. Survey will be generated to all agencies to begin this collection. Kickoff meeting scheduled for 6/17/2025 and follow-up 6/20/2025. | Promptness of agencies to provide the information back to Evident Change. Pre-trial and diversion supervision is being discussed. There are differing opinions related to the intent to collect and use information in the study. | None noted | None noted | N/A | N/A | N/A | No End Date
Deliverable 11a: Proposed State-Level Community Supervision Advisory Board | Expand and revise CSAC membership through legislative change | Legislative Change - No Committee Assigned | In Progress | None at this time | None noted | None noted | None noted | N/A | N/A | N/A | No End Date
| Expand budget for CSAC through legislative change | Legislative Change - No Committee Assigned | In Progress | None at this time | None noted | None noted | None noted | N/A | N/A | N/A | No End Date
| Provide CSAC recommendations to legislature regarding collaborative decision-making and oversight shift | Legislative Change - No Committee Assigned | In Progress | None at this time | None noted | None noted | None noted | N/A | N/A | N/A | No End Date
Deliverable 11b: Review and Reassess the Workload Study | Continue to work on selecting a vendor and launching study - DOC to fund | DOC - No Committee Assigned | In Progress | None at this time | None noted | None noted | None noted | N/A | N/A | N/A | No End Date
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per DOC Commissioner Response