## timeline update
MINNESOTA DEPARTMENT OF CORRECTIONS WORKLOAD STUDY ESTIMATED PROJECT PLAN: Compressed original timeline with goal to provide study results sooner; moving parts ot the Phase 1 data collection (e.g. operational costs) to occur later in the project timeline to accomodate moving up the workload study earlier in the project timeline | EC=Evident Change LT=Leadership Team (MN reps) DC=Design Committee
PHASE/TASK/DELIVERABLE *Project Deliverables | LEAD/ RESPONSIBILITY | YEAR 1 | [11 empty] | YEAR 2
|  | Jun '25 | Jul '25 | Aug '25 | Sep '25 | Oct '25 | Nov '25 | Dec '25 | Jan '26 | Feb '26 | Mar '26 | Apr '26 | May '26 | Jun '26 | Jul '26 | Aug '26 | Sep '26 | Oct '26 | Nov '26 | Dec '26 | Jan '27 | Feb '27 | Mar '27 | Apr '27 | May '27
PHASE ONE | [21 empty] | EXTRA MONTHS FROM ORIGINAL PROJECT TIMELINE
Identify project leadership team/project kickoff*
Data sharing, data sources, and data collection*
Develop practice survey | EC/LT
Disseminate practice survey and collect responses | EC/LT
Survey analysis; develop case classification/practice inventory | EC
Develop data sharing agreements (if needed) /Data request for aggregate case data | EC with LT review/approval
Identify data elements, sources and collection methods for determining operational costs | EC/LT | [7 empty] | extended original timeline to prioritize time study
Collect data on operational costs | EC | [7 empty] | extended original timeline to prioritize time study
Literature review on comparative workload findings | EC | [7 empty] | extended original timeline to prioritize time study
Review, Synthesis, and Reporting*
Analyze caseload data by agency | EC
Develop inventory/county classifications | EC
Approximate operational costs | EC with LT review/approval
Develop Phase 1 report: may exlude summaries of Phase I activities that are pushed out later in timeline | EC with LT review/approval
PHASE TWO
Workload study design*
Identify workload design committee | LT
Draft workload data collection tools | EC with LT review/approval
Workgroup meetings with Design Committee | EC/DC; EC will facilitate
Determine study participants | EC/LT
Develop/finalize study methods: sampling, tools, training materials | EC with DC/LT review/approval
Obtain data on staff leave time usage and allotment
Training* | EC | [10 empty] | late March/early April
Data collection and entry*
Data analysis and results*
Analyze workload data | EC
Present preliminary results with leadership team | EC/LT
Phase 2 report | EC with LT review/approval
PHASE THREE
Final report*
Review current funding formula | EC
Update capitated rate formula | EC with LT review/approval
Provide formulas for updating FTE estimates and capitated rate | EC

## timeline original
TABLE 1
MINNESOTA DEPARTMENT OF CORRECTIONS WORKLOAD STUDY ESTIMATED PROJECT PLAN
PHASE/TASK/DELIVERABLE | YEAR 1 | [11 empty] | YEAR 2
| Jun '25 | Jul '25 | Aug '25 | Sep '25 | Oct '25 | Nov '25 | Dec '25 | Jan '26 | Feb '26 | Mar '26 | Apr '26 | May '26 | Jun '26 | Jul '26 | Aug '26 | Sep '26 | Oct '26 | Nov '26 | Dec '26 | Jan '27 | Feb '27 | Mar '27 | Apr '27 | May '27
PHASE ONE
Identify project leadership team/project kickoff*
Data sharing, data sources, and data collection*
Finalize list of data sources
Develop data sharing agreements
Collect caseload data, operational cost information, supervision policy/practice, and comparative workload findings
Review, Synthesis, and Reporting*
Analyze caseload data by county
Approximate operational costs
Develop inventory/county classifications
Develop Phase 1 report
PHASE TWO
Workload study design*
Identify workload design committee
Design workload study forms/procedures
Training*
Data collection and entry*
Data analysis and results*
Analyze workload data
Determine FTE required
Phase 2 report
PHASE THREE
Final report*
Review current funding formula
Update capitated rate formula
Provide formulas for updating FTE estimates and capitated rate