## Slide 1: Partnership Program for Spring Leaf-Off Imagery
March 7, 2012

## Slide 2: Agenda for Today’s Meeting
Introductions and Overview
Project Specifications
Acquisition Region(s)
Control Targets
Project Status
Partnership Opportunities & Schedule

## Slide 3: Steering Committee
Steve Kloiber – MnDNR
  Primary funding partner; technical guidance
Chris Cialek – MnGeo
  Project management, coordination, contracting
Pete Jenkins – MnDOT
  Control target coordination; technical guidance

## Slide 4: Overview
Statewide project to collect leaf-off color imagery over 5 years
Spurred on by DNR efforts to update wetlands mapping
0.5-meter (20-inch) nominal resolution
Offer local partnership options to buy-up at improved 1-foot res.

## Slide 5: Project Specifications Four Spectral Bands
Near IR
Red
Green
Blue
Color Infrared
Natural Color

## Slide 6: Project Specifications – Leaf-Off

## Slide 7: Project Specifications - Format
Ortho-rectified quarter quad (tif)
Compressed county mosaic (jp2)
Digital stereo pairs (tif)

## Slide 8: What Resolution?
Cost vs. benefit
Managing risk
  Tight time window
  Large, complex project
  Manage the number of variables/requirements

## Slide 9: Project Specifications - Resolution
50-cm or 30cm

## Slide 10: Resolution Comparison
12-inch GSD
6-inch GSD
1 inch = 200 feet (1:2400)
1 inch = 100 feet (1:1200)
1 inch = 50 feet (1:600)

## Slide 11: Project Specifications – Positional Accuracy
Map Scale | Ground Sample Resolution | ASPRS Accuracy 95% (NSSDA) (ft)
1:1500 | 0.15 m (6-inch) | 3.06
1:3000 | 0.30 m (1-ft) | 6.12
1:5000 | 0.50 m | 10. 0
1:10000 | 1.00 m | 20.1
Tested 95% Accuracy
Northeast 2009 = ±11.5 ft
East-Central 2010 = ±4.40 ft
South 2011 = ±4.65 ft

## Slide 12: Central Acquisition - 2013
14.2 Million Acres

## Slide 13: Northwest Acquisition – (2014?)
10.5 Million Acres

## Slide 14: 2008 FSA Target Inventory

## Slide 15: 2011 Target Requirements
Two ways to capture target data
Targets (2008)
Physical features

## Slide 16: Single Leg Template

## Slide 17: Completed Target

## Slide 18: Physical Features

## Slide 19: Documentation
2008 FSA Observation Sheet
Use the same form
Pictures are necessary
Will share data with FSA

## Slide 20: What is Needed?
Existing targets need to be re-painted
New targets for counties with low numbers
Follow up with documentation

## Slide 21: SAIP Partnership Opportunities
Standard Statewide coverage:
  ½ meter (1.6 feet)
  Four band; leaf off
  Stereo and ortho (no provision for oblique at this time)
Buy-ups offer:
  Increased resolution/detail
  Improved accuracy
  Complete specific area of interest
  Volume pricing

## Slide 22: SAIP Partnership Opportunities 2
How?
  Joint Powers Agreement
  Interagency Agreement
  Purchase Order

## Slide 23: 2010 Metro Imagery Partnerships
DNR
Metropolitan Council
Rice County
USGS/NGA
MMCD
MnGeo
Dakota County
Scott County
CONTRACT
INTERAGENCY AGREEMENT
PURCHASE ORDER
JOINT POWERS AGREEMENT
INFORMAL AGREEMENT

## Slide 24: Estimated Cost at Three Resolutions
 | 1/2-meter | 1-foot | 6-inch
State contribution | $ 17 | $ 17 | $ 0
County contribution | $ 0 | $ 28 | $ 133
Total cost/square mile | $ 17 | $ 45 | $ 133

## Slide 25: Comparative Costs
 | 1/2-meter | 1-foot | 6-inch
Wisconsin 2010 (WROC) | $ 342 | $ 752 | $ 3002
Maine 2012 | $242* | $ 582 | $ 1412
MINNESOTA BUY-UP | $ 01 | $ 281 | $ 1331
2 foot resolution
1 ASPRS Accuracy Class I
2 ASPRS Accuracy Class II

## Slide 26: Estimated Cost and Compactness
 | 1-foot Large & Compact | 1-foot Small & Scattered
State contribution | $ 17 | $ 0
County contribution | $ 28 | $ 47
Total cost/square mile | $ 45 | $ 47
 | MURRAY COUNTY | 
To county line: | 745 sq. mi. X $47 = | $35,000
To quad line: | 1,035 sq. mi X $28 = | $29,000

## Slide 27: Spring Aerial Imagery Program Partnerships 2009 – 2011
Chart: 
| PROGRAM FUNDS | OTHER STATE | FEDERAL | REGIONAL | COUNTY
PROGRAM FUNDS OTHER STATE FEDERAL REGIONAL COUNTY | 640015 | 111373 | 124227 | 74500 | 137899

## Slide 28: Orthoimagery Collaboration 2009-2011

## Slide 29: SAIP Orthoimagery Collaborations 2009-2013

## Slide 30: Tentative Schedule
2012
March – May: Partnership information meetings
November: Letters of intent
December: RFP issued
2013
January – March: Proposals due/evaluated, final vendor negotiations, award made, partnership Joint Powers Agreements executed
March – May: Field observations, control point refresh, flights
May – November: Data delivered evaluated; QA/QC
December: Final delivery, acceptance

## Slide 31: Request for Proposals (RFP)

## Slide 32: Contract

## Slide 33: Field Contributions

## Slide 34: Data Management
Quarter quadrangle GeoTiffs, county mosaics, stereo, metadata
Data storage at DNR, partner organizations, back-up at MnGeo
Publicly available
Accessible through Web Mapping Service

## Slide 35: Aerial Imagery Viewer

## Slide 36: http://www.mngeo.state.mn.us/chouse/wms/geo_image_server.html
Chart: Ortho Imagery Access Requests
| N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F
Leaf-off Ortho Imagery Access Requests | 4710 | 327885 | 421393 | 425789 | 606841 | 687163 | 638840 | 692699 | 304302 | 643380 | 933165 | 809691 | 793375 | 744737 | 1135361 | 1657423

## Slide 37: http://www.mngeo.state.mn.us/chouse/airphoto/spring2009-2015.html

## Slide 38: Spring Leaf-Off Imagery for Minnesota
THANK YOU FOR ATTENDING
Q & A
steve.kloiber@state.mn.us
651.259.5164
chris.cialek@state.mn.us
651.201.2481
peter.jenkins@state.mn.us
651.366.3457